## Slide 1
East Cambridgeshire District Council
Go Live Information Pack
Simon Parker
Local Authority Delivery Manager
Allison Bradbury
Head of Local Land Charges Implementation

## Slide 2
The local authority go live pack sets out key information about the local authority and the migration process of their Local Land Charges service to HM Land Registry.
The pack will be shared with the local authority Senior Responsible Owner (SRO) for final sign off prior to issue to HM Land Registry’s Programme SRO and Chief Executive Officer (CEO) to formally approve notice being served on the local authority.
The pack will act as a formal record and point of assurance that both HM Land Registry and the local authority are satisfied that all activities have been completed in order to accurately populate and maintain the HM Land Registry Register.
Purpose
2

## Slide 3
The sign off meeting between East Cambridgeshire District Council and HMLR took place on 26 October 2022. I can confirm that all business readiness checks have been completed.
Data quality checks have passed subject to 6 charges not loading for final quality checks. Of those charges 1 was cancelled, 1 had a missing address, 1 financial charge is being investigated and 3 invalid geometries have been fixed. They will be checked once the API is switched on.
The geometric accuracy check revealed 92 positional errors and 105 extent errors. 56 were corrected, 3 have been cancelled and 138 charges were deemed to be correct. All charges will be checked when the API is switched on.
The sample test passed with 3 position errors and 2 extent errors – of those 3 have been corrected and 2 were deemed to be correct.
Search comparison exercise – 107 searches were sampled. The local authority results revealed 88 charges not contained in the HMLR register – of those 77 charges were found on re searching the register due to a referencing anomaly. 4 charges were not legitimately migrated and the remaining charges were missing due to local practice on the local authority result and have been accounted for.
The HMLR register revealed 149 charges not contained in the local authority results – this is predominantly due to a referencing anomaly with the remainder affected by large extents normally filtered out by the local authority.
The dataset held by East Cambridgeshire is highly digital but the migration took longer than anticipated due to the Community Infrastructure Levies (CILs) being recorded in a different system – the link between that system and IDOX did not work and configuration was required from IDOX. Once the link was repaired each CIL had to be reviewed and accepted onto the register. This work took just under a year hence a longer migration for a digital dataset.
Point data affected 1200 charges – the local authority agreed to have the points deleted.
The IDOX API will be used to keep the register up to date.
The local MPs who will be informed of the transfer of responsibility are Rt Hon Lucy Frazer QC MP – Minister of State for Levelling up, Housing and Communities and the Rt Hon Stephen Barclay – Secretary of State for Health and Social Care – Stephen Barclay approved the transition payment scheme and the LLC four year migration plan.
All other senior stakeholders have been informed within the local authority that the transfer is due to take place and customers have been made aware locally that
the service will transfer to HMLR.
I am satisfied that all checks have been undertaken and that East Cambridgeshire is ready for the transfer of responsibility.
Sign off summary
3

## Slide 4
Local authority overview
4
Local authority | East Cambridgeshire District Council |  |  |  | 
Address | The Grange, Nutholt Lane, Ely Cambridgeshire CB7 4EE |  |  |  | 
CEO | John Hill |  |  |  | 
Notice to be served on | John Hill, Chief Executive |  |  |  | 
SRO | Maggie Camp, Director Legal Services |  |  |  | 
Operational Lead | Paula Holmes, Local Land Charges and Paralegal |  |  |  | 
Serve notice date | 7 November 2022 |  |  |  | 
Proposed go live date | 5 December 2022 |  |  |  | 
Local authority information |  |  |  |  | 
Data type | Software supplier | Total number of charges migrated | LLC residential fee | Turnaround times * | Operating model
Digital | Idox | 46,052 | £22.40 | 7-8 days | API
Delivery |  |  |  |  | 
Migration supplier | HMLR |  |  |  | 
Delivery Model | HMLR Delivered |  |  |  | 

## Slide 5
Data overview
5
Data lifecycle overview |  | 
Number of charges extracted from LA |  | 46,052 (final extract)
Number of charges deleted |  | 4 (1 failed to load due to missing spatial, since cancelled, 3 others cancelled in response to FQA)
Number of charges amalgamated |  | 0
Number of charges created |  | 0 (other than BAU register activity)
Final number of charges |  | 46,049 will be loaded into the HMLR register This figure is 46,052, less: 1 missing spatial failing to load (as above), 2 extracted ‘migration’ records that will come through when the API is switched on (1 had a missing address, 1 was incorrectly categorised and will be fixed via a business rule) Charges cancelled as a result of FQA will be removed via an API transaction once switched on
HMLR sign off |  | 
Name | Rich Evans | 
Role | Business Analyst | 
Signed |  | 
Date | 25/10/2022 | 

## Slide 6
Final quality checks
7
Final quality Checks |  |  |  |  |  | 
Number of charges in HMLR LLC Register |  | 46,046* |  |  |  | 
Quality criteria | Quality description |  | Method of check | AQL | Outcome | Comments
Completeness* | Are all valid charges migrated |  | See Data Overview & Search Comparison | 100% | See comments | There are 6 charges that did not load for final quality checks due to : 1 x cancelled charge, 1 x missing address, 1 x Financial charge which is being investigated. 3 x invalid geometries which have been fixed and will be loaded into production prior to serve notice.
Commission | Are there any duplicate charges or replicated data attributes |  | Holistic | 95% | Pass 99.99% | 1 error where the town has been duplicated in the address
Classification | Have Charge Types & Charge Sub-categories been allocated & associated correctly |  | Holistic | 99% | Pass 100% | 
Conceptual | Adherence to LLC Practice Guides or agreed Business Rules |  | Holistic | 95% | Pass 99.97% | 
Domain | Adherence to wider rules |  | Holistic | 97% | Pass 99.96% | 
Geometric Accuracy (position) | Acceptable relationship between the land affected by the charge and the position of the geometry |  | Inspection Tests and Random Sample | 99% | Pass | See Geometric Accuracy Summary
Geometric Accuracy (extent) | Acceptable relationship between the land affected by the charge and the extent of the geometry |  | Inspection Tests and Random Sample | 99% | Pass | See Position summary Notes
Temporal Validity | Order of date attributes |  | Holistic | 95% | Pass 100% | 
Topological consistency | Acceptable geometric representation of features |  | Holistic | 100% | See comments | As per ‘Completeness’. 3 charges failed to load due to geometry issues but these have been rectified and will be loaded into production prior to serve notice

## Slide 7
Final quality checks
7
Geometric Accuracy Summary |  |  |  |  |  |  |  | 
Number of charges in HMLR LLC Register |  | 46,046* |  |  |  |  |  | 
Inspection test |  |  |  |  |  |  |  | 
A series of automated tests was used to assess the characteristics of all charge geometries in the LA dataset and identify those with the highest potential for having errors in their position and/or extent. This identified 2,266 charges which were all physically inspected. |  |  |  |  |  |  |  | 
Inspection test Outcome |  |  |  |  |  |  |  | 
Number of charges inspected | Test | Number of errors found |  | Total errors | Outcome |  |  | Comments
2,266 | Position | 92 |  | 197 | All spatial errors were inspected by the LA: 56 have been corrected 3 have been cancelled 138 were deemed to be correct |  |  | The corrected charges will be checked when the API is switched on. The high number of charges deemed to be correct was due a high number of new developments where the LA use nearby addresspoints to provide the charge address.
1,800 | Extent | 105 |  |  |  |  |  | 
Statistically valid sample |  |  |  |  |  |  |  | 
A statistically valid random sample was taken from the remainder of the dataset that had not been physically inspected. Each charge had the position and extent of the geometry assessed, with the outcome of each test evaluated independently against the 99% AQL threshold. |  |  |  |  |  |  |  | 
Population size (total charges minus inspection tests) |  | Sample size | Sample size | Sample size |  |  | Max number of errors to achieve AQL for each test | 
16,986 |  | 315 | 315 | 315 |  |  | 6 | 
Sample test Outcome |  |  |  |  |  |  |  | 
Test | Number of errors found |  |  | Outcome |  | Comment |  | 
Position | 3 |  |  | Pass |  | Of the 5 errors found, 3 have been corrected and will be checked when the API is switched on. 2 errors were deemed to be correct |  | 
Extent | 2 |  |  | Pass |  |  |  | 

## Slide 8
Search comparison
7
Search comparison: Overview |  |  |  |  |  |  |  |  |  |  | 
A sample of 107 Local Land Charge search results completed by the Local Authority (LA) between August 2021 and July 2022 was obtained by HMLR. The searches revealed 585 charges on the Local Authority register. These searches were replicated by HMLR using the Local Land Charge data that has now been transformed and migrated into the HMLR register; 641 charges were found. All discrepancies were investigated and resolved, giving a high degree of confidence the HMLR register fully and accurately reflects the register supplied and used by the LA at point of migration. |  |  |  |  |  |  |  |  |  |  | 
Search comparison output (HMLR/QA against the migrated data set) |  |  |  |  |  |  |  |  |  |  | 
Number of charges that were an exact match between the LA/PSC results and the HMLR register |  | 495 |  | Number of charges revealed on the LA/PSC results but were not found on HMLR register (A) |  | 88 |  | Number of charges revealed on HMLR register, but not on LA/PSC results (B) |  |  | 149
(A) Justification for charges excluded from HMLR register |  | All charges excluded from the HMLR register were fully investigated and justified. 77 charges were found when re-searched on the register. The reason the searches were not initially found was principally due to a referencing anomaly. 4 charges have legitimately not been migrated. 2 of the omissions related to the 6 charges that did not load into staging. 1 omission was for a financial charge which has now been paid and is no longer on the register. The remaining 4 omissions related to LA practice/error on LA result. |  |  |  |  |  |  |  |  | 
(B) Justification for charges included on HMLR register |  | The charges revealed on HMLR register but not on the LA search result were principally due to the referencing anomaly and accounted for 87 of the commissions. The remainder was mainly a result of clipping adjoining properties when searching spatially; and large extents that are filtered out of the LA search result. |  |  |  |  |  |  |  |  | 
Non-legitimate exclusions (number and justification) |  | None |  |  |  |  |  |  |  |  | 
HMLR Quality report sign off |  |  |  |  |  |  |  |  |  |  | 
Name | Gareth Robson | Role | Senior Geospatial and Data Officer |  | Signed |  | Gareth Robson |  | Date | 25/10/22 | 

## Slide 9
Live Service sign off
7
Live Service |  |  |  |  |  |  | 
All checks have been carried out in relation to system readiness between HMLR and the LA |  |  |  |  |  |  | 
Contact details and escalation points for LA provided |  |  |  |  |  |  | 
Working arrangements with other originating authorities have been agreed and are understood |  |  |  |  |  |  | 
Overview of live service reporting and monitoring have been provided |  |  |  |  |  |  | 
Acceptance into the live service is approved |  |  |  |  |  |  | 
HMLR live service sign off |  |  |  |  |  |  | 
Name | Mark Edwards | Role | Service Manager | Signed | M Edwards | Date | 25/10/22

## Slide 10
Local authority sign off meeting
Meeting details |  |  | 
Date | HM Land Registry attendees | Local authority attendees | 
26/10/2022 | Allison Bradbury, Head of Local Land Charges Implementation Simon Parker, Delivery Manager | Maggie Camp, Director Legal Services Paula Holmes, Paralegal & Local Land Charges Naomi Matthews, Local Land Charges | 
Readiness signed off by local authority |  |  | 
The local authority confirm that the data provided to HM Land Registry is its complete LLC register |  |  | 
Where HM Land Registry have assisted in the creation of spatial data, the local authority confirm that the spatial extents created accurately reflect the extent of the land affected by each charge. |  |  | 
In the event of data issues affecting the register and associated data integrity, HM Land Registry reserves the right to disable access to the register for search purposes for the duration of the issue. In the event of a data integrity issue, every effort should be made to resolve the issue in a timely manner and resume normal service. |  |  | 
The local authority confirm that a process is in place to keep the Authority’s LLC register and HM Land Registry’s LLC Register aligned during the notice period. |  |  | 
The local authority confirm that all the necessary activities in order to migrate their Local Land Charges Service to HM Land Registry have been completed. |  |  | 
The local authority confirm that a process is in place to maintain HM Land Registry’s LLC Register following the migration of the service to HM Land Registry. |  |  | 
Name | Maggie Camp | Signed | 
Role | Director Legal Services | Date | 4th November 2022
7