## Delivery Plan
[7 empty] | REVIEW AT REGULAR CATCH-UP MEETINGS |  | Status Indicators | 1 | Started
[10 empty] | 2 | Ongoing
[10 empty] | 3 | In checking
[10 empty] | 4 | Complete
Review Schedule and Progress Notes
Key Activities | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Owner | Review Due Date | Updates |  |  | Status
Start-up:
Local authority signs and returns Collaboration Agreement to HMLR | [6 empty] | LA |  |  |  |  | 0
Local authority Mobilisation Workshop | [6 empty] | HMLR |  |  |  |  | 0
Draft delivery plan agreed | [6 empty] | HMLR/LA |  |  |  |  | 0
Business Readiness Tracker populated | [6 empty] | HMLR |  |  |  |  | 0
Stakeholder analysis | [6 empty] | HMLR/LA |  |  |  |  | 0
Complete business process review | [6 empty] | HMLR/LA |  |  |  |  | 0
IT systems reviewed and changes implemented | [6 empty] | HMLR/LA |  |  |  |  | 0
Communications activities:
Update LLC webpages to advise customers of the change | [6 empty] | LA |  |  |  |  | 0
Prepare internal communications to advise other originating departments and other originating authorities' contacts of the change | [6 empty] | HMLR/LA |  |  |  |  | 0
Add advisory note to results issued within notice period | [6 empty] | LA |  |  |  |  | 0
Issue of product card with LLC1 results | [6 empty] | LA |  |  |  |  | 0
Issue email to customers confirming go live date and advising channels | [6 empty] | HMLR/LA |  |  |  |  | 0
Migration of data:
Scan paper data set | [6 empty] | HMLR |  |  |  |  | 0
Digitise scanned data set | [6 empty] | HMLR |  |  |  |  | 0
Extract digital or electronic data set | [6 empty] | HMLR |  |  |  |  | 0
Data set passes quality assurance (1) | [6 empty] | HMLR |  |  |  |  | 0
Analyse data set | [6 empty] | HMLR |  |  |  |  | 0
Address data issues | [6 empty] | LA |  |  |  |  | 0
Draft local business rules | [6 empty] | HMLR |  |  |  |  | 0
Agree draft business rules | [6 empty] | HMLR/LA |  |  |  |  | 0
Transform data set accroding to business rules | [6 empty] | HMLR |  |  |  |  | 0
Data set passes quality assurance (2) | [6 empty] | HMLR |  |  |  |  | 0
Data set is loaded into staging environment | [6 empty] | HMLR |  |  |  |  | 0
Data set is loaded into live register | [6 empty] | HMLR |  |  |  |  | 0
Serve notice | [6 empty] | HMLR
Go live | [6 empty] | HMLR
Delivery Plan [template]
Note on A6: Tabad, Josh: worth adding activity refs to the left, i.e just a number or something to help reference.

## Example Delivery Plan
A N Other LA Delivery Plan | [31 empty] | REVIEW AT REGULAR CATCH-UP MEETINGS |  | Status Indicators | 1 | Started
Key Activities | Jan | Feb | March | April | May | June | July | August | wc 31/8 | wc1/9 | wc7/9 | wc14/9 | wc21/9 | wc28/9 | wc5/10 | wc12/10 | wc19/10 | wc26/10 | wc2/11 | wc9/11 | wc16/11 | wc23/11 | wc30/11 | wc 07 Dec | wc 14 Dec | wc 21 Dec | wc 28 Dec | wc 04 Jan | wc 11 Jan | wc 18 Jan | wc 25 Jan | Owner | Review Due Date | Updates |  |  | Status
Start-up:
Local authority signs and returns Collaboration Agreement to HMLR | x | [30 empty] | LA |  |  |  |  | 4
Local authority Mobilisation Meeting | x | [30 empty] | HMLR |  |  |  |  | 4
Draft delivery plan agreed |  |  | x | [28 empty] | HMLR/LA |  | Reviewed 10/11/20 |  |  | 4
Business Readiness Tracker populated |  |  | x | [28 empty] | HMLR |  |  |  |  | 4
Stakeholder analysis |  |  | x | [28 empty] | HMLR/LA |  |  |  |  | 4
Complete business process review/mapping |  |  | x | [28 empty] | HMLR/LA |  |  |  |  | 4
IT systems reviewed and changes implemented | [7 empty] | x | [23 empty] | HMLR/LA |  |  |  |  | 4
Communications activities:
Update LLC webpages to advise customers of the change | [31 empty] | LA |  |  |  |  | 0
Prepare internal communications to advise other originating departments and other originating authorities' contacts of the change | [31 empty] | HMLR/LA |  |  |  |  | 0
Add advisory note to results issued within notice period | [31 empty] | LA |  |  |  |  | 0
Issue of product card with LLC1 results | [31 empty] | LA |  |  |  |  | 0
Issue email to customers confirming go live date and advising channels | [31 empty] | HMLR/LA |  |  |  |  | 0
Migration of data:
Scan paper data set | [31 empty] | HMLR
Digitise scanned data set | [31 empty] | HMLR
Quality Check digitised data | [31 empty] | HMLR
Extract digital or electronic data set - Initial Extract | x | [30 empty] | LA |  |  |  |  | 4
Extract digital data set - latest official Extract | [6 empty] | x | [24 empty] | LA
Data set passes quality assurance (1) Formative checks | [20 empty] | x | [10 empty] | HMLR |  |  |  |  | 3
Analyse data set | x | x | x | x | x | x | x | x | x | [22 empty] | HMLR |  |  |  |  | 4
Address data issues | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [10 empty] | LA and HMLR |  |  |  |  | 3
Draft local business rules |  |  |  |  | x | x | x | x | [23 empty] | HMLR |  |  |  |  | 3
Agree draft business rules | [22 empty] | x | x | [7 empty] | HMLR/LA |  | BR's iterated as we have gone along. Most prepared in conjunction with LA. Formal run through and agreement will be sought after Transformation to catch any new ones required for that process |  |  | 2
Final Extract? | [22 empty] | x | [8 empty] | HMLR |  |  |  |  | 0
Data set is loaded into staging environment | [24 empty] | x | [6 empty] | HMLR |  |  |  |  | 0
Data set passes quality assurance (2) includes Search Comparisons | [27 empty] | x | x | x |  | HMLR |  |  |  |  | 0
Search Comparison exercise commences | [23 empty] | x | x |  |  | x | x | x |  | HMLR/LA |  |  |  |  | 0
Data set is loaded into live register | [30 empty] | x | HMLR |  |  |  |  | 0
Serve notice | [30 empty] | x | HMLR |  |  |  |  | 0
Go live | [31 empty] | HMLR |  |  |  |  | 0

## Beta Template (hidden)
[14 empty] | REVIEW AT REGULAR CATCH-UP MEETINGS |  |  | Status Indicators | 1 | Started
[18 empty] | 2 | Ongoing
[18 empty] | 3 | In checking
[18 empty] | 4 | Complete
Review Schedule and Progress Notes
Stage | Key Activities | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | Owner | Review Due Date | Progress/Comment |  |  |  | Status
Beta Warm-up | [Authority] and HMLR meet to discuss opportunity to join Private Beta | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] has informally notifies HMLR (via Emai / Phone) it wishes to join LLC Beta | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] signs and returns Data Sharing Agreement (DSA) / Collaboration Agreement to HMLR (if not already done so) | [12 empty] | [Authority] | [5 empty] | 0
0
Beta Ready | [Authority] provides HMLR with a copy of their data for assessments (to identify any further work required) | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] and HMLR conduct workshop to progress any data issues and confirm resolution | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] and HMLR complete 'time-in-motion' study to establish resourcing requirements | [12 empty] | [Authority] | [5 empty] | 0
| HMLR confirm available resources to assist [Authority] during Beta | [12 empty] | HMLR |  | e.g. User Research / Business Analyst |  |  |  | 0
| HMLR confirms available grant funding for participation in Beta | [12 empty] | HMLR | [5 empty] | 0
| [Authority] signs and returns Private Beta Agreement (PBA) to outline roles and responsibilities and whats expected from each party | [12 empty] | HMLR | [5 empty] | 0
| [Authority] and HMLR schedule regular Beta checkpoint meetings | [12 empty] | HMLR | [5 empty] | 0
0
Beta Migration Preparation | HMLR confirms to [Authority] that is has go-live Minimum Viable Product, and confirm Migration and Transformation date and start of Private Beta | [12 empty] | HMLR | [5 empty] | 0
| Quality issues are resolved | [12 empty] | HMLR | [5 empty] | 0
| [Authority] and/or HMLR completes Migration and Transformation of [Authority] register as per the PBA. | [12 empty] | TBC | [5 empty] | 0
| [Authority] completes required Induction and training on Beta UI system | [12 empty] | [Authority] | [5 empty] | 0
0
Conduct Beta | [Authority] is able to 'Maintain an LLC' (via. User Interface) | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] is able to 'Search and Order an LLC1' (via. User Interface) | [12 empty] | [Authority] | [5 empty] | 0
| [Authority is able to 'Maintain an LLC' (via. Application Programme Interface) if using a supplier's system | [12 empty] | [Authority] | [5 empty] | 0
0
Beta Closure | [Authority] and HMLR conduct Private Beta feedback workshop to help shape its development | [12 empty] | HMLR | [5 empty] | 0
| HMLR confirms to [Authority] that it has removed its Beta data from the test environment. | [12 empty] | HMLR | [5 empty] | 0
| HMLR disbands all scheduled meetings related to Beta. | [12 empty] | HMLR | [5 empty] | 0
0
Private Beta Closure
! Author Notes - might be worthing adding in comments sections any reasons why a particular process may need to be delayed.
! Author Notes - This plan should be owned by the LAET member associated with the LA in question.
[Authority] Beta Delivery Plan

## Authority Beta Template (hidden)
[14 empty] | REVIEW AT REGULAR CATCH-UP MEETINGS |  |  | Status Indicators | 1 | Started
[18 empty] | 2 | Ongoing
[18 empty] | 3 | In checking
[18 empty] | 4 | Complete
Review Schedule and Progress Notes
Stage | Key Activities | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | Owner | Review Due Date | Progress/Comment |  |  |  | Status
Pre-Meet
Beta Warm-up | [Authority] and HMLR meet to discuss opportunity to join Private Beta | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] has informally notifies HMLR (via Emai / Phone) it wishes to join LLC Beta | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] signs and returns Data Sharing Agreement (DSA) / Collaboration Agreement to HMLR (if not already done so) | [12 empty] | [Authority] | [5 empty] | 0
0
Beta Ready | [Authority] provides HMLR with a copy of their data for assessments (to identify any further work required) | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] and HMLR conduct workshop to progress any data issues and confirm resolution | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] signs and returns Private Beta Agreement (PBA) to outline roles and responsibilities and whats expected from each party | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] and HMLR schedule regular Beta checkpoint meetings | [12 empty] | HMLR | [5 empty] | 0
0
Beta Migration Preparation | HMLR confirms to [Authority] that is has go-live Minimum Viable Product, and confirm Migration and Transformation date and start of Private Beta | [12 empty] | HMLR | [5 empty] | 0
| Quality issues are resolved | [12 empty] | HMLR | [5 empty] | 0
| [Authority] and/or HMLR completes Migration and Transformation of [Authority] register as per the PBA. | [12 empty] | TBC | [5 empty] | 0
| [Authority] completes required Induction and training on Beta UI system | [12 empty] | [Authority] | [5 empty] | 0
0
Conduct Beta | [Authority] is able to 'Maintain an LLC' (via. User Interface) | [12 empty] | [Authority] | [5 empty] | 0
| [Authority] is able to 'Search and Order an LLC1' (via. User Interface) | [12 empty] | [Authority] | [5 empty] | 0
| [Authority is able to 'Maintain an LLC' (via. Application Programme Interface) if using a supplier's system | [12 empty] | [Authority] | [5 empty] | 0
0
Beta Closure | [Authority] and HMLR conduct Private Beta feedback workshop to help shape its development | [12 empty] | HMLR | [5 empty] | 0
| HMLR confirms to [Authority] that it has removed its Beta data from the test environment. | [12 empty] | HMLR | [5 empty] | 0
| HMLR disbands all scheduled meetings related to Beta. | [12 empty] | HMLR | [5 empty] | 0
0
Private Beta Closure
[Authority]
Beta Delivery Plan