## Migration Ready checklist
Theme |  | Not ready at all | Score |  |  |  | Fully ready | Level required to be 'Pre-Migration Ready' | Level required to be 'Migration Ready' | Scale | Supporting collateral
|  |  | 1 | 2 | 3 | 4
People readiness indicators – capacity and willingness | Engagement | No Senior level LA engagement to date (Director or Assistant Director) and/or change in senior personnel risking continuity. No buy in to 'SRO collaborative agreement'. |  |  |  |  | LA Senior Responsible Owner (Director or Assistant Director level) visible, supportive of and accountable for the local change. 'SRO collaborative agreement' signed and received. | 2 | 4 | 1. No Senior level LA engagement to date (Director or Assisitant Director) and/or change in senior personnel risking continuity. No buy in to 'SRO collaborative agreement' 2. Initial Senior level LA engagement underway and broad support identified.Understanding of requirement to sign 'SRO collaborative agreement' 3. LA Senior Responsible Owner (Director or Assistant Director level) engaged and understands change required. Intent to sign 'SRO collaborative agreement' given. 4. LA Senior Responsible Owner (Director or Assistant Director level) visible, supportive of and accountable for the local change. 'SRO collaborative agreement' signed and received. Operational Lead and supported team mobilised and ready to commence work. | SRO Collaborative Agreement
| Leadership | No single operational lead in place and/or changes in personnel risking continuity. |  |  |  |  | Operational lead in place and demonstrably engaged in planning (and nominated deputy). | 2 | 4 | 1. No single operational lead in place and/or changes in personnel risking continuity 2. Plans being made to identify operational lead and/or impact of any personnel changes being considered 3. Operational lead identified and initially engaged in planning activity 4. Operational lead (and nominated deputy) in place and demonstrably engaged in planning and agreeing migration milestones on the Delivery Plan | Stakeholder grid
| Resource | No dedicated resource identified to carry out data improvement work and/or work with HMLR Delivery Team to address tactical issues. |  |  |  |  | Tactical resource identified and briefed on role to work with HMLR Delivery Team. | 2 | 4 | 1. No dedicated resource identified to carry out data improvement work and/or work with HMLR Delivery Team to address tactical issues 2. Plans underway to identify dedicated resource to carry out data improvement work 3. Tactical resource identified by LA but not engaged about their role supporting data improvement work and migration activity 4. Tactical resource identified and briefed on role to work with HMLR Delivery Team during migration | Migration RACI
| Resistance/ sentiment | Evidence of resistance or concern about change, undermining smooth engagement and planning with programme (continued failure to meet, provide information in a timely manner). |  |  |  |  | No evidence of resistance - collaborative engagement and planning underway. Representatives express a positive attitude to change initiatives and/or a recognition that change is normal and a commitment to engage positively. | Not critical for Pre-Migration or Migration Ready - can be worked on further during Service Migration activity |  | 1. Evidence of resistance or concern about change, undermining smooth engagement and planning with programme (continued failure to meet, provide information in a timely manner) 2. Some evidence of resistance or concern about change, at times undermining engagement and planning activity 3. Limited evidence of resisitance - representatives are generally engaging in a collaborative way and any resistance can be dealt with through reassurance and planning 4. No evidence of resistance - collaborative engagement and planning underway. Representatives express a positive attitude to change initiatives and/or a recognition that change is normal and a commitment to engage positively | Stakeholder Grid
| Stakeholders | Details of stakeholders not provided and/or no recognition of the need for support beyond LLCO team. |  |  |  |  | Comprehensive list of stakeholders (internal and external) that need to be involved in or aware of the migration process mapped out and role requirements articulated. | 2 | 4 | 1. Details of stakeholders not provided and/or no recognition of the need for support beyond LLCO team 2. Broad understanding of stakeholders that will need to be engaged with during migration activity, but specific requirements still not clear 3. Detailed understanding of stakeholders that will play a role in migration activity, along with better understanding of individual requirements at project level 4. Comprehensive list of stakeholders (internal and external) that need to be involved in the migration process mobilised and role requirements articulated | Stakeholder Grid
| Training | Training needs analysis not started and/or evidence of significant gaps in knowledge/ understanding to be addressed. |  |  |  |  | Training needs analysis undertaken and no significant knowledge/expertise gaps remain. | Not critical for Pre-Migration or Migration Ready - can be determined during Service Migration activity |  | 1. Training needs analysis not started and/or evidence of significant gaps in knowledge/ understanding to be addressed 2. Training needs analysis started and there is awareness of any significant gaps in knowledge/ understanding 3. Training needs analysis complete and plans in place to address any significant gaps in knowledge/ understanding 4. Training needs analysis undertaken and no significant knowledge/expertise gaps remain | Training Needs Analysis
Process and complexity indicators | Delivery Plan | No planning undertaken for transition and/or significant concerns regarding the scale of the task. |  |  |  |  | Agreed detailed Delivery Plan in place, with identifed resources for work to be undertaken and no concerns about local ability to deliver requirements. | 2 | 3 - detailed Delivery Plan, and supporting resources, to be agreed at mobilisation meeting in Service Migration | 1. No planning undertaken for transition and/or significant concerns regarding the scale of the task 2. Planning underway to develop high level delivery plan and understanding of resources and suppliers required to deliver migration 3. High level delivery plan agreed, setting out broad phases of delivery and provisional delivery date. Resources and suppliers required within each phase understood and included in plan 4. Agreed detailed Delivery Plan in place, with identifed resources for work to be undertaken and no concerns about local ability to deliver requirements | Delivery Plan
| Live service | Live service arrangements not understood or planned for to date. |  |  |  |  | Confirmed plan in place for how LA will update/maintain register in live service and no concerns regarding how this will be resourced. | 2 | 3 - if live service choices change, this can be re-planned for in Service Migration | 1. Live service arrangements not understood or planned for to date 2. Discussions have begun to determine options for live service 3. Initial agreement made for live service plans and resource options considered 4. Confirmed plan in place for how LA will update/maintain register in live service and no concerns regarding how this will be resourced | To Be process map
| Terms of Collaboration | No Terms of Collaboration in place. |  |  |  |  | Terms of Collaboration signed by both LA and HMLR. | 4 | 4 | 1. No Terms of Collaboration in place 2. Terms of Collaboration sent to LA for processing 3. LA agreement to sign obtained in principle 4. Terms of Collaboration signed by both LA and HMLR | Terms of Collaboration
| Collaboration Agreement | No Collaboration Agreement in place. |  |  |  |  | Collaboration Agreement signed by both LA and HMLR. | 1 | 2 | 1. No Collaboration Agreement in place 2. Collaboration Agreement sent to LA for processing 3. LA agreement to sign obtained in principle 4. Collaboration Agreement signed by both LA and HMLR | Collaboration Agreement
Data and supplier indicators | Data sources | No process mapping undertaken and limited knowledge of data sources. |  |  |  |  | Detailed process mapping work completed, all known data sources identified and all non-digital data scanned and ready for digitisation. | 1 | 4 | 1. No process mapping undertaken and limited knowledge of data sources 2. High level process mapping undertaken and initial data sources understood 3. Detailed process maps being developed, main data sources identified and plans to digitise non-digital data scoped and agreed 4. Detailed process mapping work completed, all known data sources identified and all non-digital data scanned and ready for digitisation or already digitised | As Is process maps (with identified data sources) Data Assessment refresh document
| Data improvement | Data extract not provided and no or limited understanding of data issues. |  |  |  |  | Data Analysis Dashboard created and data improvement work completed | 1 | 3 - if data fix work is underway, we could decide to proceed at risk with LA | 1. Data extract not provided and no or limited understanding of data issues 2. Data extract provided and analysed to provide understanding of data issues. Feedback given to LA and action plan to address agreed 3. Data improvement work being actively undertaken 4. Data Analysis Dashboard created and data improvement work completed | Data Analysis Dashboard
| Incumbent supplier | Incumbent supplier not identified or engaged to date, despite demonstrable reliance on provider for LA's preparation and extraction of data and live service. |  |  |  |  | LA engaged and supplier arrangements in place to support obtaining an official data extract. | 2 | 4 | 1. Incumbent supplier not identified or engaged to date, despite demonstrable reliance on provider for LA's preparation and extraction of data and live service 2. Incumbent supplier identified but not engaged with to date 3. Incumbent supplier identified and engaged with but contractual arrangements not complete to enable data extracts to be obtained 4. LA engaged and supplier arrangements in place to support obtaining an official data extract | As Is process maps (with identified data sources) Data Assessment refresh document
| Software | LA is using supplier software which needs upgrading to enable an offical extract to be produced. |  |  |  |  | LA has the latest version of supplier software which includes the toolset to enable an official extract to be produced. | 3 | 4 | 1. LA is using supplier software which needs upgrading to enable an offical extract to be produced 2. Initial work being scoped between LA and HMLR to plan for required software upgrade including resource requirements to support upgrade work 3. Defined plan in place for software upgrade including installation date and resources are in place to support 4. LA has the latest version of supplier software which includes the toolset to enable an official extract to be produced | As Is process maps (with identified data sources) Data Assessment refresh document
Other | Risk | Additional LA-specific significant risk identified with potential to undermine engagement and delivery. | Yes - risk identified |  | No risk or identified risk mitigated |  | No additional significant risk threatening engagement and delivery identified at this stage. | N/A | 3 and 4 | Identified risk(s) to be assessed and mitigation actions put in place on an individual basis. Lead Delivery Manager to determine if LA can proceed to 'Migration Ready' status. | Migration Risk and Issues Log
| Migration Effort score |  | 99 |  | 0 - 20 |  |  |  |  | Migration effort to be assessed via LA Data Scorecard methodology and actions required to raise score to tolerated level put in place on an individual basis. Lead Delivery Manager to determine if LA can proceed to 'Migration Ready' status. | Data Scorecard
Proposed Delivery Model